GRADUATION PROJECT DOCUMENTATION

# Project Planning & Management

Healthcare Analytics for Patient Outcomes & Hospital Performance

Project proposal, schedule, roles, risks, and project success measures

Team Members:

1)   Eslam Mamdouh (Team Leader)

2)   Assem Ayman

3)   Zainab Shady

4)   Mariam Khaled

5)   Abdullah Masoud

Selected project title Healthcare Analytics for Patient Outcomes & Hospital Performance.

Evidence and completeness note This document uses the project details and team assignments shared in the planning conversation. Items not provided (such as lecturer feedback and the official grading rubric) remain identified as pending rather than invented.

# 1. Project Overview

The project is a healthcare analytics graduation project focused on understanding patient outcomes and evaluating hospital performance. The team will use a synthetic healthcare dataset to build an end-to-end workflow: understand and profile source tables, clean and transform data with Python, design and implement relational and dimensional models in SQL, and develop interactive Power BI dashboards supported by clearly defined KPIs and analytical findings.

## 1.1 Project Context and Data

The working dataset is identified in the conversation as General Healthcare Dataset V5 / V5 Final Raw and is synthetic educational data, not real patient records.

The dataset contains 12 subject-area tables: Patients, Encounters, Hospitals, Departments, Hospital_Departments, Appointments, Lab_Tests, Treatments, ICU_Admissions, Deaths, Staff, and Daily_Hospital_Stats.

The agreed data workflow is to preserve the raw source, profile and clean it with Python, build SQL models and analytical queries, and then use the validated outputs in Power BI.

The Daily_Hospital_Stats coverage was intentionally kept at 180 days; the team explicitly chose not to extend the period in the final dataset revision to avoid disturbing related tables.

## 1.2 Problem Statement

Healthcare information is distributed across patients, encounters, appointments, laboratory tests, treatments, ICU admissions, deaths, hospitals, departments, staff, and daily operational statistics. A consistent data preparation and analytical modeling process is needed to examine patient outcomes alongside hospital performance, including patient flow, length of stay, department activity, bed occupancy, and resource utilization. The project addresses this analytics and information-organization need using the synthetic dataset available to the team.

## 1.3 Objectives

Understand the meaning, grain, keys, and quality issues of every source table.

Use Python and pandas to profile, clean, transform, and validate the data while documenting decisions and before/after quality results.

Design the relational model, normalize the operational structure where appropriate, and build the analytical Fact/Dimension model (the intended overall design is a Galaxy / Fact Constellation schema).

Create the SQL database and implement the agreed tables, relationships, keys, and constraints; then answer data questions with join-based analysis and organize reusable views and SQL scripts.

Build Power BI data models, measures, KPIs, and dashboards for hospital overview, operations, patient/clinical analytics, staff/departments, and appointments as allocated across the team.

Present the workflow, data limitations, analytical findings, and project outputs in a final PowerPoint presentation.

## 1.4 Scope

| In Scope | Out of Scope / Limitations |
| --- | --- |
| Python profiling, cleaning, transformation, validation, and selected visualizations. | Clinical diagnosis, medical treatment recommendations, or claims of clinical effectiveness. |
| SQL ERD, normalization, relational implementation, Fact/Dimension modeling, Galaxy schema, queries, joins, and views. | Integration with a live hospital information system; no such integration was specified. |
| Power BI data modeling, Power Query, DAX measures, KPIs, and interactive dashboards. | Production deployment, guaranteed uptime, or real-user adoption measurement; these were not specified. |
| Synthetic-data analysis of encounters, appointments, tests, treatments, ICU, deaths, hospitals, staff, departments, and daily operations. | Treating synthetic patterns as evidence about real patients or real hospitals. |

Important limitation All analytical findings must be described as findings from synthetic educational data. They must not be presented as real clinical evidence or as recommendations for patient care.

# 2. Project Plan and Timeline

The following schedule reflects the timeline stated by the team in the conversation. It records the planned work and deadlines; it does not claim that each milestone has already been completed.

| Phase / Task | Dates | Main activities | Deliverables |
| --- | --- | --- | --- |
| Python — Task #1: Initial Table Understanding | 01–04 Oct 2026 | Understand each assigned table, its purpose and grain, and identify initial null, duplicate, and data-type concerns. No data cleaning is performed. | Table explanations and preliminary issue notes. |
| Python — Task #2: Profiling & Cleaning-Rule Design | 05–08 Oct 2026 | Formal table profiling (Milestone 1), followed by documented cleaning and transformation rules (Milestone 2). No implementation yet. | Profiling notes, issue register, and agreed cleaning-rule matrix. |
| Python — Task #3: Cleaning (Part 1) | 11–13 Oct 2026 | Implement initial cleaning for assigned tables, prepare working notebooks, and create first cleaned copies. | Initial cleaned tables, notebooks, and before/after quality summaries. |
| Python — Task #3: Transformation & Validation (Part 2) | 13–15 Oct 2026 | Complete agreed transformations, cross-table checks, and final Python handoff, following the previously discussed project schedule. | Validated prepared tables, unresolved-issue notes, and final Python handoff. |
| SQL — Task #4: Design & Modeling | By 26 Oct 2026 | Preliminary Fact/Dimension identification; relational modeling and relations; normalization; dimensional refinement and Galaxy schema; final full schema. | ERD, normalized relational design, Galaxy schema, and final schema documentation. |
| SQL — Task #5: Database Setup | By 30 Oct 2026 | Create the database and implement tables, relations, and constraints. | Database creation script, table definitions, relationships, and constraints. |
| SQL — Task #6: Data Questions & Analysis | By 02 Nov 2026 | Prepare data questions and perform SQL analysis using joins. | Documented questions, SQL join/analysis queries, and interpreted findings. |
| SQL — Task #7: Views & SQL Gathering | By 06 Nov 2026 | Create views and gather/organize the SQL work in a clear repository. | SQL views and organized SQL scripts/query collection. |
| Power BI | 07–30 Nov 2026 | Power Query, data modeling, DAX, KPI development, dashboards, integration, testing, and review. | Interactive Power BI report with documented KPI definitions. |
| Finalization & PowerPoint | 01–10 Dec 2026 | Finalize project outputs, prepare the final presentation, rehearse, and complete the handover package. | Final PowerPoint presentation and project handover package. |

## 2.1 Python Work Breakdown

| Window | Milestone | Expected output |
| --- | --- | --- |
| 01–04 Oct 2026 | Task #1 — Initial Table Understanding | Understand the assigned table, grain, key structure, and likely quality issues. Explain findings to the group; no cleaning. |
| 05–08 Oct 2026 | Task #2 — Profiling & Rule Design | Milestone 1: formal profiling. Milestone 2: define and document cleaning/transformation rules; no cleaning implementation in this task. |
| 11–13 Oct 2026 | Task #3 — Initial Cleaning (Part 1) | Execute core cleaning steps and produce first cleaned copies, notebooks, and quality summaries. |
| 13–15 Oct 2026 | Task #3 — Transformation & Validation (Part 2) | Continue the previously planned transformation, cross-table validation, and final Python handoff. |

Task #1 and Task #2 are two separately documented parts of the same data-understanding and preparation stage. Task #1 is initial familiarization only. Task #2 is the more complete profiling and rule-design activity. Neither task includes actual data cleaning.

### 2.1.1 Task #1 — Initial Table Understanding

| Member | Assigned table(s) | Required understanding |
| --- | --- | --- |
| Eslam | Patients; Encounters; Deaths | Understand each table and its purpose; explain the grain; identify likely NULL, duplicate, and data-type problems and discuss possible handling approaches. No cleaning or data changes. |
| Assem | ICU_Admissions; Treatments | Understand the table and grain; identify likely NULL, duplicate, and data-type issues; explain the table to the group. No cleaning. |
| Zainab | Hospitals; Daily_Hospital_Stats; Lab_Tests | Understand the tables and grains; identify likely NULL, duplicate, and data-type issues; explain the findings. No cleaning. |
| Mariam | Hospital_Departments; Appointments | Understand the tables and grains; identify likely NULL, duplicate, and data-type issues; explain the findings. No cleaning. |
| Abdullah | Departments; Staff | Understand the table and grain; identify likely NULL, duplicate, and data-type issues; explain the findings. No cleaning. |

Task #1 output: a clear verbal or written explanation for the group covering the assigned tables, their grain, and the initial data-quality concerns. This is an understanding task only; no cleaning is required.

### 2.1.2 Task #2 — Profiling & Cleaning-Rule Design

Milestone 1 — Understanding & Profiling: document what exists in each table. Profiling is descriptive; problems are recorded, not fixed at this stage.

| Member | Assigned table(s) | Required profiling |
| --- | --- | --- |
| Eslam | Patients; Encounters; Deaths | Table purpose; grain; PK/FK; data types; null profile; duplicate profile; unique values; initial business rules. |
| Zainab | Hospitals; Daily_Hospital_Stats; Lab_Tests | Table purpose; grain; PK/FK; data types; null profile; duplicate profile; unique values; initial business rules. |
| Assem | ICU_Admissions; Treatments | Table purpose; grain; PK/FK; data types; null profile; duplicate profile; unique values; initial business rules. |
| Abdullah | Departments; Staff | Columns; grain; PK/FK; null count; unique count; basic distributions. |
| Mariam | Hospital_Departments; Appointments | Columns; grain; PK/FK; null count; unique count; basic distributions. |

Milestone 2 — Cleaning Rules & Transformation Design: for every identified issue, specify the affected table/column, the problem, the rule, and the planned action. The rules below preserve the assignments shared by the team.

| Member | Table(s) | Cleaning / transformation rule to define |
| --- | --- | --- |
| Eslam | Patients | Gender normalization; flag invalid age values; standardize city formatting; define missing-age strategy. |
| Eslam | Encounters | Diagnosis strategy; Comorbidities bridge-table strategy; readmission validation; date logic. |
| Eslam | Deaths | Validate consistency between death records, death dates, and encounter outcomes. |
| Zainab | Hospitals | Hospital-type normalization; occupancy validation; total/occupied/available bed rules. |
| Zainab | Daily_Hospital_Stats | Duplicate hospital-date investigation; occupancy validation; missing operational metrics. |
| Zainab | Lab_Tests | Test-type handling; units; distinguish numeric from qualitative results. |
| Assem | ICU_Admissions | ICU-duration validation; ventilation/dialysis rules; APACHE missing-value handling. |
| Assem | Treatments | Treatment type; dose; batch; side-effects handling. |
| Abdullah | Departments; Staff | Department naming; role/certification formatting; working-hours validation. |
| Mariam | Hospital_Departments | Duplicate hospital-department pairs; valid hospital and department keys. |
| Mariam | Appointments | Status normalization; date/time handling; no-show logic. |

Example rule format: Patients.gender — map M / Male / male to Male; map F / Female / female to Female; keep blank values as Missing/Unknown. Patients.age — flag values below 0 or above 110 rather than deleting the patient. Patients.city — strip spaces and standardize casing. Encounters.diagnosis — define a split/bridge-table strategy. Encounters.readmission_flag — map mixed Boolean formats to 1/0. Deaths.death_date — retain missing values and document them.

Task #2 output: completed profiling notes and a cleaning-rule matrix. Actual data cleaning belongs to Task #3.

### 2.1.3 Task #3 — Python Cleaning

Part 1 — 11–13 October 2026. Execute the documented basic cleaning rules, handle formats and invalid values, and produce an initial cleaned version of every assigned table. The objective is an initial clean copy, not the final analytical analysis.

| Member | Assigned table(s) | Cleaning actions and required handover |
| --- | --- | --- |
| Eslam | Patients; Encounters; Deaths | Patients: load with pandas; inspect row/column counts, NULLs, and duplicates; standardize gender and city and remove extra spaces; flag invalid ages without deleting patients. Encounters: standardize core text; inspect admission_date and discharge_date; review missing diagnosis, insurance_type, and outcome; handle comorbidities under agreed rules without deleting original content. Deaths: standardize text; inspect death dates and missing values; review duplicates and linking keys. Handover: three initial cleaned tables, an end-to-end notebook, and before/after row-count, NULL, and duplicate summary. |
| Zainab | Hospitals; Daily_Hospital_Stats; Lab_Tests | Hospitals: inspect data types, NULLs, and duplicates; standardize text spacing/casing; flag implausible total_beds, occupied_beds, and available_beds without arbitrary correction. Daily_Hospital_Stats: standardize date in the working copy; detect hospital_id + date repeats; check bed/occupancy relationships and missing operational metrics. Keep the 180-day period. Separate exact duplicates from conflicting records; do not arbitrarily delete different records. Lab_Tests: convert numeric values to suitable types; standardize test_type, result, and unit; flag unit/value mismatches; review encounter/staff keys. Handover: three initial copies and a report of fixed issues and items requiring review. |
| Assem | ICU_Admissions; Treatments | ICU_Admissions: inspect types, NULLs, and duplicates; review ICU entry/exit dates; validate icu_stay, ventilation_days, and dialysis_days; flag remaining implausible values without inventing replacements. Treatments: standardize spaces/text; inspect type_treatment, number_dose, and number_batch; distinguish medicines from procedures; verify administered_at can be handled as a time value. Handover: notebook for both tables, two initial copies, and a summary of standardized and flagged values. |
| Abdullah | Departments; Staff | Departments: check primary key and duplicates; standardize department-name spacing; review missing values and alternate spellings. Staff: check staff_id and duplicates; standardize text; convert working hours to numeric; inspect date_hire, date_leave_sick, and implausible working hours. Handover: two initial copies, a before/after NULL and duplicate summary, one staff-by-role chart, a simple notebook, and a quality summary. |
| Mariam | Hospital_Departments; Appointments | Hospital_Departments: check duplicates by hospital_id + department_id; verify referenced hospitals and departments exist; review missing keys. Appointments: check appointment_id duplicates; standardize text; convert appointment dates; inspect status and encounter_id and consistency between appointment status and encounter. Add/recalculate lead_days only if required by the agreed definition. Handover: two initial copies, notebook, quality summary, and appointment-status distribution chart. |

Task #3 Part 1 handover: each member submits the assigned initial cleaned table copies, a runnable notebook, and a concise quality summary. Zainab must preserve the 180-day Daily_Hospital_Stats window and document exact duplicates separately from conflicting same-hospital/same-date records. Abdullah and Mariam also provide the requested preliminary charts.

Part 2 — 13–15 October 2026. Continue with the previously planned transformation and validation follow-through: derived fields where agreed, cross-table checks, before/after summaries, and a final prepared-data handoff. The exact Part 2 member-by-member checklist was not separately reissued in the latest task message.

## 2.2 SQL Task #4 Design Order

create an initial analytical view of the required facts and shared dimensions.

create the ERD and define tables, primary/foreign keys, relationships, and cardinalities.

refine the operational/relational schema through 1NF, 2NF, and 3NF where appropriate.

after the data-cleaning stage, finalize Fact/Dimension tables, grain, conformed dimensions, bridge tables, and the Galaxy / Fact Constellation schema.

document both the normalized relational model and the final analytical model.

Normalization reduces structural redundancy and insertion/update/deletion anomalies in the operational (OLTP) schema. It does not, by itself, fix NULL values, duplicate source records, or logically invalid values; those are handled through data profiling and cleaning. Dimensional modeling is a separate analytical design step and is refined after the cleaned data is available.

# 3. Task Assignment and Roles

The project team consists of five named members: Eslam Mamdouh (Team Leader), Assem Ayman, Zainab Shady, Mariam Khaled, and Abdullah Masoud. The current work allocation assigns the heavier technical/design streams to the members identified in the earlier team plan and gives bounded, meaningful workstreams to the other members. The assignments shown below are the current working allocation.

| Member | Python ownership | SQL ownership | Power BI / Presentation ownership |
| --- | --- | --- | --- |
| Eslam Mamdouh — Team Leader | Patients, Encounters, Deaths; patient-lifecycle and cross-table review. | Coordinate ERD/design; review normalization; lead advanced encounter, readmission, and outcome queries; integration review. | Core data model, core DAX/KPIs, Executive Overview; project narrative, architecture, coordination, and final presentation flow. |
| Zainab Shady | Hospitals, Daily_Hospital_Stats, Lab_Tests. | Database architecture/implementation coordination; keys and constraints; Fact/Dimension implementation; hospital-operations queries. | Hospital Operations dashboard; technical pipeline section in the presentation. |
| Assem Ayman | ICU_Admissions, Treatments. | Advanced analytical SQL, joins, CTEs/window functions as needed, ICU and treatment questions. | Patient/Clinical Analytics dashboard; analytical findings and interpretation. |
| Abdullah Masoud | Departments, Staff. | Basic joins/aggregations and quality-assurance queries for departments and staff. | Staff/Department visuals; presentation formatting support. |
| Mariam Khaled | Hospital_Departments, Appointments. | Appointment analysis, simple views, and referential-integrity checks. | Appointments module; filters, navigation, user-experience support, and proofreading. |

## 3.1 Collaboration and Review

Each table group has a primary owner responsible for the notebook, cleaning rules, and outputs.

Eslam, Zainab, and Assem review high-risk work involving cross-table keys, dates, encounter grain, ICU logic, financial measures, and Fact/Dimension joins, with the relevant table owner involved.

Abdullah and Mariam own defined deliverables in their assigned workstreams; their work is reviewed, not treated as optional assistance.

Shared cleaning functions should be reused where their behavior matches the intended rule. Table-specific cleaning logic must remain table-specific when a common function would change results.

The team should preserve the raw V5 source and save prepared outputs separately, documenting row counts and transformations.

# 4. Risk Assessment and Mitigation Plan

| Risk | Potential impact | Mitigation / response | Primary attention |
| --- | --- | --- | --- |
| Synthetic data limitations | Patterns may not represent real-world clinical or hospital behavior. | Label the dataset synthetic; restrict conclusions to the generated data; avoid clinical claims or treatment recommendations. | Eslam + all members |
| Residual data-quality issues | Missing, inconsistent, duplicate, or multi-value fields may distort analysis. | Profile first; document cleaning rules; preserve raw values where needed; report before/after counts and unresolved issues. | All table owners |
| Different fact grains / join fan-out | Joins between encounters, tests, treatments, and appointments can multiply rows and inflate counts or bills. | Document each Fact grain; aggregate child facts independently before combining; validate row counts and totals after joins. | Eslam, Zainab, Assem |
| Cross-table relationship errors | Orphan records or inconsistent hospital/encounter links can invalidate findings. | Run PK/FK and cross-table validation after cleaning and after loading to SQL. | Eslam, Zainab, Assem |
| Uneven availability and skill levels | Heavy tasks may become bottlenecks or less experienced members may be blocked. | Split milestones into small deliverables; assign meaningful bounded ownership; use reviewer/owner pairing. | Eslam (Team Leader) |
| Schedule slippage between phases | Late Python outputs can delay SQL; late SQL can delay Power BI. | Respect the agreed handoff dates; provide partial outputs at each milestone; escalate blockers early. | Eslam (Team Leader) |
| Uncontrolled dataset regeneration | Repeatedly regenerating the source can reintroduce issues or break completed work. | Treat V5 as the frozen raw baseline; handle ordinary issues in the cleaning pipeline; change the source only through a reviewed, documented decision. | Eslam + reviewers |
| Unclear definitions of KPIs | Different members may calculate the same metric differently. | Maintain a shared KPI definition with formula, source table, grain, filter logic, and validation query. | Eslam, Zainab, Assem |
| Presentation overstates results | Synthetic analytics could be mistaken for clinical evidence. | State the synthetic-data limitation in the presentation and dashboards; distinguish descriptive/operational analysis from clinical decisions. | Eslam + Assem |

# 5. Project KPIs and Success Measures

The following are project-delivery and analytical-quality measures that fit the agreed prototype. Numeric targets beyond the confirmed number of source tables were not specified by the team, so they are left for team approval rather than invented.

| KPI / Measure | How it is assessed | Target / status |
| --- | --- | --- |
| Source-table coverage | All 12 named source tables have a documented purpose, grain, key fields, and owner. | 12 of 12 tables. |
| Cleaning traceability | Each implemented cleaning rule is documented with affected columns and before/after counts. | Target to be confirmed; recommended acceptance condition: no undocumented transformations. |
| Referential integrity | Critical PK/FK relationships in the approved SQL model are checked for orphan records. | Target to be confirmed; expected design goal is zero unexplained orphans in final analytical tables. |
| Analytical correctness | SQL outputs reconcile with validated table-level counts and do not double-count facts. | All approved analysis queries checked. |
| KPI definition coverage | Each Power BI KPI has a documented formula, source, grain, and filter behavior. | All KPIs displayed in the final report. |
| Dashboard functionality | Filters, slicers, relationships, and visuals respond consistently to the intended date/hospital/department context. | All report pages tested before presentation. |
| Reproducibility | Python cleaning notebooks/scripts can be rerun from the preserved raw source to regenerate the prepared outputs. | Repeatable run documented. |
| Presentation readiness | All five members can explain their assigned work and the end-to-end project flow. | Final rehearsal completed by 10 Dec 2026. |

Why uptime and user-adoption KPIs are not included The scope discussed is a data analytics prototype using Python, SQL, and Power BI. No deployed web application, production service, real user population, or uptime monitoring was specified. Therefore system uptime and user adoption cannot be honestly measured as current project KPIs. Dashboard responsiveness may be evaluated during testing, but no numeric response-time target has been agreed.

# 6. Project Deliverables

| Stage | Deliverables |
| --- | --- |
| Python | Task #1 table-understanding notes; Task #2 profiling records and cleaning-rule matrix; Task #3 Python notebooks, initial cleaned tables, before/after quality summaries, validation notes, and preliminary plots. |
| SQL | Task #4 ERD, normalized relational schema, Galaxy schema, final schema documentation; Task #5 database, relations, and constraints; Task #6 data questions and join-based analysis; Task #7 views and organized SQL scripts. |
| Power BI | Power Query transformations; analytical data model; DAX measures; KPI definitions; interactive dashboards and tested report pages. |
| Finalization | PowerPoint presentation; final project package; any additional documentation explicitly requested by the lecturer/program. |

# 7. Assumptions and Items Pending Confirmation

Official lecturer requirements, deployment expectations, and grading rubric: not supplied in the conversation.

Final Power BI page count and exact KPI list: planned modules are reflected, but final page count and KPI definitions remain subject to team approval.